## Template change log & approval
GTS MANAGEMENT SYSTEM
URS Generic WBS, OBS and RACI Matrix
83410775-PRJ-CAN-EN-012 |  |  |  | Template
Please refer to GTS Management System for: • The process activity to which this document is attached • The criteria (country, company…) applicable to this document • The latest version in force, unless otherwise specified in your context
If you cannot find this document in GTS Management System, it means that it is not applicable to you.
Abstract
The generic WBS, OBS and RACI matrix to be used for URS projects. The generic templates provided in this document will need to be adapted to the specific project needs.
Log of changes
Revision | Description |  |  | Publication date
001 | First Issue Peer review reference: TCTS-CHR-15-007 |  |  | 2015-02-27
002 | Generic CBS tab added. Generic WBS L6 tab added |  |  | 2015-10-06
003 | Modified the flow chart for Generic OBS-Domestic and Generic OBS-Export. Removed the revision level on the top right of the embedded Chart on the Generic OBS and CBS. Changed Written By Name. Updated tailoring tab |  |  | 2016-02-03
004 | In support of CR 038790 : Generic WBSL6 tab: Added WBS activity 1.1.7 Non-Technical Requirements Management WBS Instructions: Removed document Revision numbers & added comment for table to be checked. Generic OBS – Domestic tab: OBS updated to include DDQS Stakeholders and reflect changes in Engineering & Services Project Organization. Generic OBS – Export tab: tab removed. Generic RACI tab: Added R&O Management, & Non-Technical Requiremnts Mgt Tailoring Sheet : tab removed Log of changes and approval: removed as duplication from Abstract & Log of changes tab |  |  | 2017-05-09
005 | Migration to new Template All tabs modified to include new Solution Deployment and Services (SDS) Organization Further engineering WBS/CBS/RACI changes to come in revision 006 of this document. |  |  | 2017-09-12
006 | Generic OBS: removal of ATS role. Addition of PPTM role. R&O Manager outside of POM responsibility. HSE Manager from PM's responsibility to Deployment Manager's responsibility. Generic WBSL5: Removal of costs placeholders "Contigencies" & "Others like Direct Selling Costs". Merge of Solution Engineering & System IVVQ Workpackages. Sligth amendments to Solution Deployment workpackage. Generic WBS: Visio reflecting changes to Generic WBSL5 tab Generic CBS: Visio reflecting changes to Generic WBSL5 tab Generic RACI: Table reflecting changes brought to the OBS & WBS WBS Instructions: table reflecting changes brought to the WBS |  |  | 2018-01-31
007 | Generic WBS & Generic CBS: update of WBS 5.1.2 from "Schedule Management" to "Schedule & Resource Management" Generic WBSL5: update of tab title from "WBS L6 for URS Projects" to "WBS L5 for URS Projects". Some activities renamed & renumbered, please refer to column F "Changes from previous WBS". Generic WBSL5: update of the WBS dictionnary Generic WBS, Generic WBSL5 & Generic CBS: WP 2.5 Cyber Security split in 2 WP. Generic OBS: Addition of 3 roles (Cyber Sec Authority, Cyber Sec Eng Manager, Cyber Sec Assurance Manager) and Technical Interface Leader. Adjustments in dotted lines/full lines for Safety Authority, Safety Assurance and Quality Assurance. Generic RACI: Addition of Cyber Security WPs & OBS roles. Generic CBS: Addition of "Project Closure" placeholders. |  |  | 2018-05-15
008 | Generic WBS: Visio limited to WBS L2 workpackages. Detailed WBS: consolidation of procurement activities under WP1.4 (activities "3.8.2.6 OnBoard Material Procurement" and "3.8.3.6 WS/Central Material Procurement" have been removed. Detailed WBS, Generic CBS, Generic RACI: Remove Stakeholders Mgt & NTR Mgt in WP1. Generic OBS & Generic RACI : Addition of Chief Engineer role. Detailed WBS : Update of Safety Engineering & RAM Engineering WPs breakdown. Generic WBS, Detailed WBS, Generic CBS, Generic RACI: Project Configuration Management merge into 3.1.5 Solution Configuration Management. Configuration Manager reporting to SEM and Site Configuration Manager reporting to Deployment Project Manager. Generic WBS, Detailed WBS, Generic CBS, Generic RACI: Cost Control Management moved from 1.1.1 to 1.2. Generic WBS, Detailed WBS, Generic CBS, Generic RACI: Transfer of Cyber Security development from WP 2 to WP 3.9. Generic WBS, Detailed WBS, Generic CBS, Generic RACI: changes to Solutions Deployment WPs (Additional breakdown to Infrastructure Design, Addition of Warehouse & Logistic and Decommissioning WPs, Split T&C from Deployment) & Services WP (removal Customer Support Mgt WP) Detailed WBS: more breakdown provided to Operations Training & Maintenance Training. Generic WBS, Detailed WBS, Generic CBS, Generic RACI: Specialty Engineering created & left blank. Will be used in the future for non-core CBTC activities like Artificial Intelligence or Bid Data Analytics. Generic OBS: Safety Engineering Manager has been renamed Project Safety Manager Closure CR052329 |  |  | 2019-02-28
009 | Generic WBS, Detailed WBS, Generic CBS, Generic RACI: WP2 renamed to Technical Safety Generic OBS: changes in Safety OBS Generic RACI: Safety Authority & Project Design Authority are ""(C)onsuled" regarding "Independent Validation" artefacts (CR052044) Generic WBS, Detailed WBS, Generic CBS, Generic RACI: WP1.6 Project Configuration Management added Generic WBS, Detailed WBS, Generic CBS, Generic RACI: WP3.9b Cyber IT Design added (and System Platform Software & Integration renumbered 3.9a) Detailed WBS : limitation of WP3 to WBS Level 2 activities. Generic OBS: Chief Engineer has been ranmed Chief Engineering Architect due to local regulations |  |  | 2021-02-02
010 | Generic WBS, Detailed WBS, Generic CBS, Generic RACI: WP4 created which consolidates DCS, Network & Cyber activities. (WP to be either WP3.8 or WP4 depending on a set of rules captured on the right of the WBS & CBS) Generic WBS, Detailed WBS, Generic CBS, Generic RACI: Training WP transferred from 5.1 to WP 5.9. Generic WBS, Detailed WBS, Generic CBS, Generic RACI: Publication & Archives WP transferred from 5.1 to WP1.6. Generic WBS, Detailed WBS, Generic CBS, Generic RACI : Project Configuration Management WP removed Generic OBS and Generic RACI: changes to Deployment OBS Generic OBS and Generic RACI: Safety OBS updated Generic WBS, Detailed WBS, Generic CBS: changes in WP3 Engineering Workpackages |  |  | 2022-02-25
011 | Detailed WBS: changes in details of WP 4.1 Generic OBS: correction in the dotted line reporting of SAM to PSM Generic OBS: Project Admin & Publications are reporting to the Data Manager. Detailed WBS: Deletion of "Test & Commissioning Support" activity which should not have been listed. |  |  | 2022-06-28
012 | Updated to Hitachi template as per QUAL-5663 |  |  | 2025-05-28
Internal signature
Actor | Role / Job title | Name | Signature | Signature date
Written by | URS PMO Manager | Thomas Delevacque |  | 2022-06-28
Verified by | CCM | Patricia Lavergne |  | 2022-06-28
Approved by | 5.2 CPO | Francois Coursault |  | 2022-06-28
Hitachi Rail – Internal
This document may not be reproduced, modified, adapted, published, translated, in any way, in whole or in part, or disclosed to a third party without the prior written consent of HITACHI RAIL
|  | © Hitachi Rail Limited 2025. All rights reserved. |  | Template: 87201589-QCI-GRP-EN-014

## Generic WBS
Generic WBS
-
Hitachi Rail – Internal
This document may not be reproduced, modified, adapted, published, translated, in any way, in whole or in part, or disclosed to a third party without the prior written consent of HITACHI RAIL
| © Hitachi Rail Limited 2025. All rights reserved. | Template: 87201589-QCI-GRP-EN-014
Please note that the WBS revision number (bottom right) is to be kept for version traceablility.
This WBS has been built in accordance with the WBS Golden Rules. For details, please refer to :
https://wiki.corp.thales/display/ThAB/WBS+Golden+Rules
Major changes from last revision
Text
Minor updates (renaming, renumbering)
*
*
Data Communication Systems to be as WP4 only if:
- WP hours > 10% Eng hours
- WP hours > 5% total project hours
- Visible deliverables to the Customer
Otherwize it will be treated as WP3.8.
Decision to be taken at Bid Phase & confirmed at Project Launch Review.

## Detailed WBS
Detailed WBS for URS Projects
-
| (In red, changes from last revision) |  |  |  | WBS Dictionary
WBS Level | WBS Code | WBS Name | Reports to | Changes from previous WBS | WBS activity Description | Owner | WBS input(s) | WBS output(s) | Quality Requirement(s) | Acceptance Criteria | Earned Value Definition (defined only at level 2)
0 | 0 | URS Transport Project
1 | 1 | Program Management | 0
2 | 1.1 | Program Management | 1 |  | • Management baseline and plan (WBS/OBS/work-packages, schedule, cost estimates, risks, data management, etc.) • Personnel management (skills, workloads, resources). • Program monitoring (status report, progress, cost, financing, etc.), performance report (progress report). | PM Assisted by POM, Risk Manager, Data Manager & Project Assistant | Notification to Proceed (NTP) Complete Bid Package WP agreements Project Management Plan (if any) | Project Management Plan Deliverable CDRL list Customer & Internal Stakeholder reports (Project Schedule, Data Management Plan, Project Review Dashboard) Customer Sign-off - Provisional Acceptance Project Closeout Checklist | Compliance to GTS MS Manage Project (5.2) process and re-use of Group or entity tools & template (WBS/OBS/work-packages,...) | Continues throughout project to handover to SD&S Group for Warranty Services | Level of Effort
2 | 1.2 | Cost Control Management | 1 |  | • Management cost baseline and financial reporting | PCC | WBS structure | Project Review Dashboard |  |  | Level of Effort
2 | 1.3 | Contract Management | 1 |  | • Preparation of contractual correspondence, notifications • Negotiation of penalties, contract changes, claims, commercial issues | Contract Manager | Contract documents, compliance matrix | Project Close-out Checklist |  |  | Level of Effort
2 | 1.4 | Procurement | 1 |  | • Make-or-buy strategy • Analysis and monitoring of procurement and supply chain risks / site quality control | Acquisition Project Manager | Bid Package including schedule, equipment list, technical requirements Contractual requirements | Project Procurement Plan IPP (cost, lead time, risks, supplier strategy, export restrictions) Inspection and Testing Plan |  |  | Level of Effort
2 | 1.5 | Quality Assurance | 1 |  | • All quality activities across entire program system:, quality assurance, auditing. • Monitoring of norms and standards applicable to the contract | Quality Manager | Contract documents, compliance matrix | Quality Plan Audit, Assessment, and Analysis Report |  |  | Level of Effort
2 | 1.6 | Publications and Archives | 1 | moved from 5.2 | • Publication & Archiving of Internal documentation | Publications WPM |  | Publication and archiving of documents
1 | 2 | Technical Safety | 0
2 | 2.1 | Safety Engineering | 2 |  | • Conduct hazard identification studies (HAZOP/HAZID) and hazard analyses (FHA, FTA) and derive safety requirements. • Perform safety design reviews (system, software and hardware) and safety analyses to ensure compliance to safety design principles and requirements. • Review verification and validation plans, test procedures and reports to confirm coverage by test and analysis. • Record and track hazards (Hazard Log), control measures, design and verification and validation evidence and confirm the hazard risks are tolerable. • Prepare safety appraisals, safety cases (design and implementation) and safety memos to demonstrate the system is safe for its intended purpose. | Safety Engineering Manager | Project Management Plan, SEMP, SW Dev Plan, HwEM Plan, Sys Data Mgt Plan, Sys Verification plan, Sys Validation plan, System Test Plan Customer Requirements Specification, System Architecture Specification, System Requirements Specification, Subsystem Requirements Specification Interface Control Documents System Detailed Design Operation Manuals and Guides Test Procedures, Test Reports Migration Plan Software Architecture Specification, Software Detail Design Hardware Requirements Specification, Hardware Detail Design, Hardware Schematics, Interface Schematics, Wiring Drawings | System Safety Plan Preliminary Hazard Analysis System Hazard Analysis Interface Hazard Analysis HAZOP/HAZID Reports Functional Safety Analyses Hardware Safety Studies Software Safety Studies FMEA/FMECA Reports Fault Tree Analysis Hazard Log Safety-related Application Conditions Report Safety Cases/Reports (product, platform, generic application, specific application – design and implementation) Technical Support - Integrated Design Team, Safety Design Reviews Support CCRB/PCRs Review and Approve Documents – Plans, Test Procedures Safety Analyses and White Papers |  | Delivery of safety case and approval of safety certificate by Safety Authority URS.
2 | 2.2 | Safety Assurance | 2 |  | Assure the safety of our delivered solutions by performing Safety Assurance Gate Reviews (SAGRs), independent safety audits/assessments, and Root Cause Analysis (RCA) investigations (as needed) for commercial projects and for internal product development in order to identify issues related to technical safety and applied processes. | Safety Assurance Manager | RAM and Safety Plans Engineering Plans (including System Design, System Operations, HW and SW) IVQ Plans Safety and Hazard Analyses Safety Case | Internal Safety Assurance Plan (per project or product) Safety Assurance Gate Review (SAGR) Checklist SAGR Findings Log Internal Safety Audit/Assessment Report Safety Certification Readiness Review (SCRR) Checklist Root Cause Analysis Report (if required) | CENELEC Standards - EN 50126-1:1999, EN 50128:2011, EN 50129:2003, EN 50157:2010 AREMA IEE 1474.1 | - Internal Safety Assurance Plan approved by Safety Assurance director - Applicable DDQS gate passes with Safety Assurance acceptance - Internal Safety Audit/Assessment Reportapproved by Safety Assurance director - Safety Authority and, if applicable), external ISA acceptance of the safety case. - Root Cause Analysis Report approved by Safety Assurance director and the Hitachi Rail GTS Canada Safety Authority.
2 | 2.3 | RAMT (RAM & Testability) | 2 |  | • Perform RAM analyses to confirm system performance and compliance to RAM targets. • Review system architecture and hardware design (FMEA/CA) to identify Single Point Failures (SPF) and Common Cause Failures (CCF). • Perform Testability Analysis to evaluate the fault detection and isolation coverage. • Perform Spare Parts Analysis for the system warranty period/system life. • Monitor the system performance during the demonstration period and produce reports. | RAM Manager | System Architecture Specification, System Requirements Specification, Hardware Requirements Specification Hardware Detail Design, Hardware Schematics Interface Schematics, Wiring Drawings Equipment Layout, Bill of Material, Equipment Family Tree Component/Part Hardware Specifications Operation Manuals and Guides | RAM Plan RAM Analysis Spare Parts Analysis Special Tools and Equipment List Testability Analysis System FMEA/CA RAM Demonstration Plan RAM Demonstration Report |  | Approval of applicable RAM documents by Design Authority and Project Manager.
2 | 2.4 | Independent Validation | 2 |  | Provides objective confirmation that a solution {element} is suitable for the intended operation in the intended environment by using planned analyses, based on evidence, to support a judgment regarding satisfaction of stakeholders’ expectations, particularly those for RAMS and Quality, as part of a determination of its overall fitness for purpose. | Independent Validator | Design Validation(s) (and Design Justification Files), Operational Concept Description(s), Service File(s), Verification Plan(s), Engineering Management Plan(s), Project (and Work Package) Management Plan(s), Quality Assurance Plan(s), Configuration Management Plan(s), Safety Plan(s), RAM Plan(s), Product Breakdown Structure, Quality Management Report(s), Configuration Management Report(s), Hazard Log(s), RAM Analyses Engineering Reviews Records & referenced artefacts | Solution Validation Plan Solution Validation Report | Validation objectives of CENELEC standards - EN50126-1:2017, EN50126-2:2017, EN50128:2011, EN50129:2018 (including applicable corrigenda and normative references) Validation objectives of IEEE standard - 1012:2016 (including applicable corrigenda and normative references) | Validation Plan agreed by Safety Authority Validation Report taken into account in Safety Case
1 | 3 | Solution Engineering | 0
2 | 3.1 | Project Engineering Management (PEM) | 3 | Renamed/added to group PEM workpackages |  | Project Management Director | Project Management Plan BID Package (Engineering Cost Estimate, Requirement Compliance Matrix, DVA) WPA Engineering Project Schedule R&O register DVA | Solution Engineering Management Plan (SEMP) WPA per Engineering WP Engineering Dashboard Contribution to: Project Schedule Contribution to: R&O Register DVA Validation of DDQS Reviews
3 | 3.1.1 | Solution Engineering Manager (SEM) | 3.1 |  | • Management Engineering baseline and plan (WBS/OBS/work-packages, schedule, cost estimates, risks, etc.) • Resource management (skills, workloads). • Engineering WP monitoring (status report, progress, cost, financing, etc.), performance report (progress report). • Management of the overall Engineering WP Schedule • Calculation & Monitoring of the critical path • update of Budget, ETC and EAC forecasts per CBS based on WPM inputs • Overall Engineering WP responsibility and lead role for opportunities and risk management efforts. | PEM Director | Project Management Plan BID Package (Engineering Cost Estimate) WPA Engineering Project Schedule R&O register | Solution Engineering Management Plan (SEMP) WPA per Engineering WP Engineering Dashboard Contribution to: Project Schedule Contribution to: R&O Register
3 | 3.1.2 | Project Design Authority (PDA) | 3.1 |  | Authority role for Product design instantiation to the project - Guarantees the integrity, relevance and feasibility of the Bids and Projects technical content, in accordance with Product Policy, adequate product re-use, Make-or-Buy Strategy, as well as the maturity of the technologies employed and the adequate assignment of Engineering teams; Challenges the Solution, has a right of audit and can trigger and organize technical reviews accordingly; Has the right to participate to or even chair the main Solution technical/engineering reviews during the execution of the bid or project; Validates the technical Risks & Opportunities assessment; Validates the Solution design by signing the Design Validation (DVa); Alerts the Division TD as needed; | PEM Director | BID Package (Requirement Compliance Matrix, DVA) DVA | Contribution to: Engineering Dashboard Contribution to: Project Schedule Contribution to: R&O Register DVA Validation of DDQS Reviews
2 | 3.2 | Solution Configuration Management (SCM) | 3 | Added. Extracted from WP3.1 | – Ensures that products comply with their requirements and are identified and documented in sufficient details to support the product life cycle, – Assures accurate product configuration information and enables product interchangeability, safe product operation and maintenance, – Facilitates orderly identification of product attributes and provides control of product information and product changes used to improve capabilities; correct deficiencies; improve performance, reliability, or maintainability; extend product life; or reduce cost, risk or liability. | Configuration Manager | Contract documents, compliance matrix, scope split with partners / customer, original proposal's CM estimates. WPA PBS (if available from the bid phase) Configuration Management Plan | * Input to Work Package Agreement * Configuration Management Plans * Input to Statement/s of Work * CM inputs (or review of CM related content) to other plans such as PMP, SEMP, QAP and etc * Project associated CM metrics and KPIs * CMP implementation * Configuration Identification (solution baselines management in CM tool) * Participation in CCBs * Configuration Status Accounting for solution level (examples: As-Delivered Data Management, CM input to Data Packs, SVDD input and etc.) * Configuration Verification & Audit (FCA & PCA, HW ECNs and FCB CM's reviews)
2 | 3.3 | Systems Engineering | 3 | WP added to group Systems Design, Signalling Design & Network Design
3 | 3.3.1 | Systems Design | 3.3 |  | • Product System Specification and Design instantiation to the project -OCD, functional design and analysis, requirements definition, SSS, SSDD, ICD, IRS, alarms, parameters, -technical support to SW, HW, IVQ, Safety, Site etc. | System Engineering Manager (SysEM/WPM) | SEMP WPA Bid Package (Requirement Compliance Matrix, DVA) Customer specification Project Schedule R&O Register Product model, product SSS, SSDD, CD, IRS, alarms, parameters, product PCRs, | OCD, SSSs, SSDDs (SyRS, SyDD, SAS), alarms, parameters, ICDs, IRS. SysDes VDD Traceability Customer Requirement up to Sub-System level Specification Contribution to: Engineering Dashboard, Project Schedule, R&O Register
3 | 3.3.2 | Signalling Design | 3.3 |  | • Product System Data Design instantiation to the project. - Defining the System Data Specification based on the System Design Requirements. - Defining Tool Requirements for tools used in the data design and configuration activities. - Producing a System Performance Analysis report. - Produce block designs, control tables, and system data input and export files. | System Engineering Manager (SysEM/WPM) | SEMP WPA Bid Package (Requirement Compliance Matrix, DVA) Product SDS, product B-rules, | System Data Management Plan, System Data Specification, Safe Braking Model, Track Block Designs, Control Tables, System Performance Analysis, SPSIM software, Data Management Toolset, System Database. Contribution to: Engineering Dashboard, Project Schedule, R&O Register
| 3.4 | Software Engineering | 3 | WP added to group SW workpackages
3 | 3.4.1 | Vehicle Software | 3.4 |  | • Product Vehicle Software instanciation to the project. - contribution to SRS/IRS (as part of Sub-System specification) - full responsability of Sw design, Sw coding,Sw/Sw integration - contribution to STP/STR (as part of the Sub-System verification) | Vehicle Sofware Engineering Manager (SwEM/WPM) | SEMP WPA Compliance matrix Build Plan/Schedule Sub-System level specifcation (SyDD) System Database (neutral files) System Architecture Document | SDP (one applicable for all SW) SRS/IRS (contribution) , SDD/IDD, Code, Unit/Module test, STP/STR (contribution) Traceability to code / test (as defined in CENELEC) VDD
3 | 3.4.2 | Wayside Software | 3.4 |  | • Product Wayside Sofware instanciation to the project. - contribution to SRS/IRS (as part of Sub-System specification) - full responsability of Sw design, Sw coding, Sw/Sw integration - contribution to STP/STR (as part of the Sub-System verification) | Wayside Software Engineering Manager (SwEM/WPM) | SEMP WPA Compliance matrix Build Plan/Schedule Sub-System level specifcation (SyDD) System Database (neutral files) System Architecture Document | SDP (one applicable for all SW) SRS/IRS (contribution) , SDD/IDD, Code, Unit/Module test, STP/STR (contribution) Traceability to code / test (as defined in CENELEC) VDD
3 | 3.4.3 | Central Software | 3.4 |  | • Product Wayside Sofware instanciation to the project. - contribution to SRS/IRS (as part of Sub-System specification) - full responsability of Sw design, Sw coding, Sw/Sw integration - contribution to STP/STR (as part of the Sub-System verification) | Central Software Engineering Manager (SwEM/WPM) | SEMP WPA Compliance matrix Build Plan/Schedule Sub-System level specifcation (SyDD) System Database (neutral files) System Architecture Document | SDP (one applicable for all SW) SRS/IRS (contribution) , SDD/IDD, Code, Unit/Module test, STP/STR (contribution) Traceability to code / test (as defined in CENELEC) VDD
3 | 3.4.4 | Environment Simulator Software (ES) | 3.4 | Added | • Product Simulator Software instantiation to the project. - contribution to SRS/IRS (as part of Sub-System specification) - full responsibility of Sw design, Sw coding, Sw integration - contribution to STP/STR (as part of the Sub-System verification) | Simulator Software Engineering Manager (SwEM/WPM) | SEMP WPA Compliance Matrix Build plan /Schedule Sub-System level specification (SyDD) System Database (neutral files), IVVQ Test Plan, Lab Requirements. System Architecture Document | SDP (one applicable for all SW) VDD, Simulator User Guide, Sub-System Simulator Requirements, Simulator Software applications utilizing the LDP and ECN process.
3 | 3.4.5 | Software Verification | 3.4 | Added | Integration & Test of all the software components (Vehicle, Wayside, Central) before transter to the IVVQ team | Simulator Software Engineering Manager (SwEM/WPM) | SEMP WPA Compliance Matrix Build plan /Schedule Sub-System level specification (SyDD) System Database (neutral files), IVVQ Test Plan, Lab Requirements. System Architecture Document | SDP (one applicable for all SW) VDD, Simulator User Guide, Sub-System Simulator Requirements, Simulator Software applications utilizing the LDP and ECN process.
2 | 3.5 | Hardware Engineering | 3 | Renamed | • Product Hardware instantiation to the project (from the Specification to the Industrialisation and Qualification) • Cover the 3 domains : Vehicle HW, Wayside/Central (including DCS), and tools HW | Hardware Engineering Director | SEMP WPAs (could be 1 to 3 depending of the project complexity) System level specifcation for Hardware (HW) and Embedded Middleware (MW) | . WPM documents (inputs to WPA, HEMP, Updated Schedule, HW Risk) . Design documents (HW and MW Requirements, HW and MW Detailed design, Electronic and Electrical Schematics/FPGA designs, Simulation analysis and FPGA test benches, Qualification test plans and reports, Interfaces Schematic diagrams) . Industrial documents (BOMs, assembly drawings, FAT procedure, Obsolescence management plan)
3 | 3.5.1 | Vehicle Design | 3.5 | Added | Vehicle Product Hardware instantiation to the project (from the Specification to the Industrialisation and Qualification) | Hardware Engineering Manager (HwEM/WPM) | SEMP WPAs (could be 1 to 3 depending of the project complexity) System level specifcation for Hardware (HW) and Embedded Middleware (MW) | . WPM documents (inputs to WPA, HEMP, Updated Schedule, HW Risk) . Design documents (HW and MW Requirements, HW and MW Detailed design, Electronic and Electrical Schematics/FPGA designs, Simulation analysis and FPGA test benches, Qualification test plans and reports, Interfaces Schematic diagrams) . Industrial documents (BOMs, assembly drawings, FAT procedure, Obsolescence management plan)
3 | 3.5.2 | Wayside / Central Design | 3.5 | Added | Wayside/Central (including DCS) Product Hardware instantiation to the project (from the Specification to the Industrialisation and Qualification) | Hardware Engineering Manager (HwEM/WPM) | SEMP WPAs (could be 1 to 3 depending of the project complexity) System level specifcation for Hardware (HW) and Embedded Middleware (MW) | . WPM documents (inputs to WPA, HEMP, Updated Schedule, HW Risk) . Design documents (HW and MW Requirements, HW and MW Detailed design, Electronic and Electrical Schematics/FPGA designs, Simulation analysis and FPGA test benches, Qualification test plans and reports, Interfaces Schematic diagrams) . Industrial documents (BOMs, assembly drawings, FAT procedure, Obsolescence management plan)
3 | 3.5.3 | Hardware Tools | 3.5 | Added | Tools Product Hardware instantiation to the project (from the Specification to the Industrialisation and Qualification) | Hardware Engineering Manager (HwEM/WPM) | SEMP WPAs (could be 1 to 3 depending of the project complexity) System level specifcation for Hardware (HW) and Embedded Middleware (MW) | . WPM documents (inputs to WPA, HEMP, Updated Schedule, HW Risk) . Design documents (HW and MW Requirements, HW and MW Detailed design, Electronic and Electrical Schematics/FPGA designs, Simulation analysis and FPGA test benches, Qualification test plans and reports, Interfaces Schematic diagrams) . Industrial documents (BOMs, assembly drawings, FAT procedure, Obsolescence management plan)
3 | 3.5.4 | Hardware Compliance | 3.5 | Added | • Defines Hw IVQ strategy in consistency with that of upper level. • Tailors Hw I&V environment (process, practices and tools) according to Country/Company and project’s requirements. • Defines HW IVQ scenarios and guaranties their implementation. • Coordinates HW IVQ activities, establishes priorities and integration logical diagrams, conducts tests, supports factory and site acceptance as well as commissioning, analyses results and transmits them to development teams. • The HwIVQM may sometimes cumulate WPM role. | HwVER / HwVAL (Hardware Integration Verification Qualification Manager (HwIVQM) As the HwEM’s delegate manages Hw Integration Verification & Qualification activities
2 | 3.6 | Integration, Test and Verification (ITV) | 3 | renumbered | • Sub-System and System Requirement Inhouse verification • Inhouse System Operational Test • Site Commissioning Procedure Preparation | IVVQ Manager or VV Manager (System and Subsystem VV Manager) | SEMP WPA System and Sub-System specification (SyRS/SyDD or SSS/SRS) SW executable / VDD Integrated Test Environment | System Verification and Validation Plan (SVVP) System Test Plan System / Sub-System Test Procedures (both inhouse and Site Procedures) System / Sub-System Test Reports, FAT Report SRVM (System Requirement Validation Matrix) System Acceptance and Commissiioning Report
3 | 3.6.1 | Core CBTC Integration, Test and Verification (ATS/STC/VOBC) | 3.6 | Added | Core ITV – Integration, test and verification of each CBTC subsystem and requirement coverage verification. The major subsystems include ATS/SMC ZC/STC/VCC and VOBC | IVVQ Manager or VV Manager (System and Subsystem VV Manager) | SEMP WPA System and Sub-System specification (SyRS/SyDD or SSS/SRS) SW executable / VDD Integrated Test Environment | System Verification and Validation Plan (SVVP) System Test Plan System / Sub-System Test Procedures (both inhouse and Site Procedures) System / Sub-System Test Reports, FAT Report SRVM (System Requirement Validation Matrix) System Acceptance and Commissiioning Report
3 | 3.6.2 | Specialty Integration, Test and Verification (Specialty ITV) and Tools Engineering | 3.6 | Added | Specialty ITV – Integration, test and verification of supporting systems and tools. Supporting systems include DCS/ViewTrac and tools include the environment simulator and SGDG Tools Engineering – Any tools required internally and externally to support the CBTC solution. Internal tools such as the SGDG (data exports) and external tools to the customer such as ViewTrac, Cab Simulators etc. | IVVQ Manager or VV Manager (System and Subsystem VV Manager) Tools SW developers | SEMP WPA System and Sub-System specification (SyRS/SyDD or SSS/SRS) SW executable / VDD Integrated Test Environment | System Verification and Validation Plan (SVVP) System Test Plan System / Sub-System Test Procedures (both inhouse and Site Procedures) System / Sub-System Test Reports, FAT Report SRVM (System Requirement Validation Matrix) System Acceptance and Commissiioning Report Production of customer tools (ViewTrac/Analytics) and internal tools (SGDG/SDM)
2 | 3.7 | Product / Platform | 0 | Added | Product activities and commitment of the Product team towards the Project. | Product WPM | Dva | Product Platform Product documents
3 | 3.7.1 | Product Development | 3.7 | Added | Product instantiation to the project (from the Specification to the Industrialisation and Qualification)
3 | 3.7.2 | Platform Development | 3.7 | Added | TOP and WP-UR / OC-UR Platform instantiation to the project (from the Specification to the Industrialisation and Qualification)
2 | 3.8 | Data Communication Systems | 0 | Added | Please refer to WP4 for details. WP4 to become WP3.9 if: - total WP hours are < 5% total project hours - total WP hours are <10% Engineering hours - there are no develiverables visible to the Customer.
1 | 4 | Data Communication Systems | 0 | Renamed
2 | 4.1 | Cyber IT / DCS / Network / Tools Design | 4
3 | 4.1.1 | Cyber Design | 4.1 | Split in 2 subWP from 4.1.1 Cyber and IT Engineering | Cybersecurity provides specialized domain knowledge on cybyersecurity engineering and assist system and other engineers develop and incorporate security design and functions into their solutions. Specific domain knowledge incluces cryptography, network zoning, intrusion detection, applicaiton security, security design partterns and all related matters to securing the CBTC solution. Examples include: Firewall configuration, Sign-on/password management, Security device configuration, security policy application etc. | Cyber Security Manager | Security Requirements Security Standards Cybersecurity Risk Assessment | Cybersecurity Management Plan Cybersecurity Risk Assessment Cybersecurity Technical Vulnerability Assessment Plan Technical Vulnerability Assessment and Penetration Testing Site Security Acceptance Testing Plan Site Security Testing Report Cybersecurity Design and Architecture Cybersecurity Solution (Software and Hardware) | IEC 62443 Framework NIST SP Series
3 | 4.1.2 | IT Design | 4.1 | Split in 2 subWP from 4.1.1 Cyber and IT Engineering | IT engineering provides IT Architecture which spec ifies Policies, Principles, Services, Standards and Guidelines and the products (Server/Middleware/Client) for CBTC Applications, CyberSecurity Applications. | Cyber Security Manager | Security Requirements Security Standards Cybersecurity Risk Assessment CBTC Application Requirements | Cybersecurity Management Plan Cybersecurity Risk Assessment Cybersecurity Technical Vulnerability Assessment Plan Technical Vulnerability Assessment and Penetration Testing Site Security Acceptance Testing Plan Site Security Testing Report Cybersecurity Design and Architecture Cybersecurity Solution (Software and Hardware)
2 | 4,1.3 | DCS Product Platform and Tool Design | 4,1 | Renamed from 4.1.4 Tools Design | It Provides Complete Generic Product Solutions to be used by the projects to support Reliable, High Available and low latency cyber-secured communication platyform for CBTC Applications. The solution will include In-House SW/COTS HW/SW. Also It designsand delivers the tools required for in-house use and/or field use for Testing , Monitoring, Debugging and Automation of the tasxks. It is also responsible for the product sustaining and maintence tasks for the legacy solutions. | Product SEM/WPM | CBTC Application Requirements Product Requirements - Cyber/IT/Networking Project Requirements - NRCs | Product DCS SRS DCS Platform RS DCS Platform Network & IT Infrastructure Design DCS Platform Application Guide
3 | 4.1.4 | Communications and Network Design | 4.1 | Merged into 1 subWP from 4.1.2 Communications Engineering & 4.1.3 Network Design | Project instantiation of the DCS product design, with project-specific functions, as applicable. Activities include DCS subsystem requirements analysis, design specification and development, as well as participation in the Integrated Design Team (IDT) at the system level. Deployment definition (plan of RF surveying, initial RF coverage estimation) as well as general design support throughout the project lifecycle are also included. Communications Engineering – all related matters to the infrastructure that carries the messages to enable communications between subsystems. Examples include: Software Define Radio Adaptation, Wired network configuration, Network Management System Adaptation, Remote SW download etc. | System Engineering Manager (SysEM/WPM) | Product SSS Product DCS SRS DCS Platform RS DCS Platform Network & IT Infrastructure Design DCS Platform Application Guide Project Customer Specifications Project SSS Project DCS SRS Project data (civil drawings, train layout, etc.) Project SEMP | Requirements coverage from DCS SRS Project DCS Network & IT Infrastructure Design Project DCS RF Survey Plan Project DCS RF Survey Report (initial estimation only) Project DCS Network & IT Infrastructure Configurations Contribution to: Engineering Dashboard, Project Schedule, R&O Register
2 | 4.2 | DCS Test and Verification | 4
3 | 4.2.1 | DCS Integration, Test and Verification (DCS ITV) | 4.2 |  | Specialty ITV – Integration, test and verification of supporting systems and tools. Supporting systems and tools include DCS/ and tools include Viewtrack, NMS, NIDS | IVVQ Manager or VV Manager (System and Subsystem VV Manager) | SEMP WPA System and Sub-System specification (SyRS/SyDD or SSS/SRS) SW executable / VDD Integrated Test Environment | System Verification and Validation Plan (SVVP) System Test Plan System / Sub-System Test Procedures (both inhouse and Site Procedures) System / Sub-System Test Reports, FAT Report SRVM (System Requirement Validation Matrix) System Acceptance and Commissiioning Report
2 | 4.3 | Cyber Security Assurance | 4
3 | 4.3.1 | Cyber Security Assurance | 4.3 |  | Reviews and approves cybersecurity product or solution deliverables | Cyber Security Assurance Manager | Security Requirements Security Standards Cybersecurity Risk Assessment | Approval of Cybersecurity / IT Engineering outputs | IEC 62443 Framework NIST SP Series
1 | 5 | Solutions Deployment | 0
2 | 5.1 | Deployment Project Management | 5 | Renamed | • Resource planning, KPIs, Dashboard reviews and management • Scheduling & Monitoring of the Deployment activities • Site Configuration Management 5.1.1 DPM Management 5.1.2 Planner (PCM) 5.1.3 Site Configuration Management 5.1.4 Local Subcon Management 5.1.5 Site Quality | Deployment Project Manager (DPM) | Site Quality | SDS Dashboard, WW resource database, R&O Register Project Schedules, milestones, LFR, Budget, As designed & As built configurations Site CM database (As-installed, As-Maintained), Report status of As-Installed Configuration to a project safety engineer. Resolve Site CM issues in cooperation with Site Deployment team, Communicate CM issues related to a PM and Project CM.
2 | 5.2 | Installation Design | 5 | Removed reference of Sys Ops / architecture / GDG Data | • HW and application design • Surveys, application design & application configuration • Designers providing support with either site travels or through usage of TARA / phone / email for all of 5.2 • DCS & Cyber Configuration | SID WPM | Systems requirements Product design ICD documents | I/O bit map Application / layouts / Interconnection drawings HW application reqmts verification Project BOMS, PBS, Bids, PICO, PPR, SOW |  |  | Number of CDRL documents delivered vs planned nbr of gates passed vs planned
2 | 5.3 | Warehouse & Logistic | 5 |  | Covers the freight cost from Customs (port/Airport/point of entry) to Customer site. | Deployment Project Manager (DPM) | BOQ
2 | 5.4 | Installation | 5 |  | Cost collector for installation activities within the equipment room, the wayside, the OCC & BOCC central equipment room and the vehicle excluding Engineering’s initial delivery of 2 Gold Std stock | Site Installation Manager |  |  |  | Acceptance by Customer
2 | 5.5 | Test & Commissioning | 5 |  | • Debugging activities effort captured in the subsystem elements • Final roll out test and customer in-service activities • DCS & Cyber Deployment | Site Deployment Manager | Site System Integration Procedures SW (informal/formal) Field Test Readiness Review passed SAT Procedures As-Designed and As-Build Configurations | System Integrated and functional PICO Testing/Report Test Track functional SAT Certificates Cutover / Operation Trial completed
2 | 5.6 | Decommissioning | 5 |  | Removal & disposal of existing hardware | Site Installation Manager |  |  |  | Acceptance by Customer
2 | 5.7 | HSE | 5 |  | Management of Health, Safety & Environment (HSE) issues including the definition of HSE standards, the training of site personnel and the audit of subcontractors & personnel to ensure that Hitachi Rail GTS Canada HSE standards are being applied. | HSE Manager | Customer Contract for HSE requirements Local regulation | HSE plans and procedures Training Plan HSE awareness trainings for onsite staff User Guides Training Course Guides Training Courses delivery HSE audits and inspections Reports Accident / Incident Assessments and reports
2 | 5.8 | Track and Civil Works | 5 |  | In case construction/civil works, activities usually outside of URS scope of work, are required on the project. | Site Installation Manager | Customer Contract Local regulation
2 | 5.9 | Training Delivery | 5 | moved from 5.1 | • Training Customers Internal & External |  | Training requirements |  |  |  | SPI / CPI
1 | 6 | Service Delivery | 0
2 | 6.1 | Warranty Support | 6 |  | • All repairs and replacements during the warranty period. • All software debugging during warranty period • Technical assistance (if applicable) | Service Delivery Manager (SDM) | Customer Contract for Services Project Close-out Issues (Punch List) Requests for support from customer RAM Analysis for (LCC) | Repairs & Replacements Technical Assistance
2 | 6.2 | Life Cycle Support | 6 |  | • Maintenance Plan preparation and submission . Service Definition Document (SDD) if applicable. . Obsolescence Maintenance Plan (OMP) if applicable | Service Delivery Manager (SDM) | Customer Contract for Services (Post Warranty) RAM analysis for (LCC) | Maintenance plan SDD (if applicable) OMP (if applicable)
2 | 6.3 | Other Services | 6 |  | • Preparation and submission of value-added Services package such as: - Health monitoring Services - Viewtrac Data collection - Condition based / predictive maintenance - …… | Service Delivery Manager (SDM) |  | Other Services
Hitachi Rail – Internal
This document may not be reproduced, modified, adapted, published, translated, in any way, in whole or in part, or disclosed to a third party without the prior written consent of HITACHI RAIL
[5 empty] | © Hitachi Rail Limited 2025. All rights reserved. | Template: 87201589-QCI-GRP-EN-014
Note on K4: Quality requirements should list any specific Quality requirements for the project for each WBS element: e.g. If Quality Assurance plan is one of the WBS element than if the project requires to be complaint with ISO standard we should list the ISO standard in this column
Note on L4: Acceptance criteria column should list the acceptance criteria for each WBS element: e.g for the above example QAP plan released under ECN and approved

## WBS Instructions
WBS Instructions
-
WBS Code | WBS Name | Description | GTS MS 2.0 reference documents name | Process # | GTS MS 2.0 Reference #
TCTS WBS | TCTS WBS
TCTS WBS.1 | Program Management |  | Manage Project CAN Procedure | 5.2 | 87200984-PRJ-GRP-EN | Comments
TCTS WBS.1.1 | Program Management | Including PMO activities, NTR management | Manage Project CAN Procedure | 5.2 | 87200984-PRJ-GRP-EN | Available on GTS MS Processes -> 5.2 PRJ -> Print
TCTS WBS.1.2 | Cost Control Management | Cost Control activities |  | 2.1
TCTS WBS.1.3 | Contract Management | Contract Management activities | Guide to contract Management Manage a contract (Procedure) | 9.8 | 87208528-LEG-GRP-EN 87201396-LEG-GRP-EN
TCTS WBS.1.4 | Procurement | Labor at this level, material is handled at subsystem level | Manage Acquisition CAN | 7.1 | 87201314-ACQ-GRP-EN | Available on GTS MS Processes -> 7.1a ACQ -> Print
TCTS WBS.1.5 | Quality Assurance | Quality Assurance Plan for an individual project | Quality Assurance Plan | 4.1 | 87211389-QCI-GRP-EN
TCTS WBS.1.6 | Publications and Archives | -Activities related to any document to be ECN'd and drawings and SW archiving | Publication and Data Records Implementation Guideline | 8.1 | 83410362-DOC-CAN-EN
TCTS WBS.2 | Technical Safety
TCTS WBS.2.1 | Safety Engineering | WPM activities - Safety Planning - Safety Management and Supervision All Safety Engineering activities performed at any stage and level of the project - Hazard Analyses - Hazard Management - Safety Analyses - Safety Case | Manage a Work Package -Safety Management Instruction - Safety Planning Guideline Safety Instruction - Hazard Management - Identify and Analyze Hazards Process - Safety Case and Safety Approval Guideline - Safe Operating Requirements & Safety Application Conditions Guideline - Specific Hazard and Safety Analysis | 5.2 6.1 4.1 | 87201255-PRJ-GRP-EN 87204905-DDQ-GRP-EN 83410196-QCI-CAN-EN 83410224-QCI-CAN-EN 87204905-DDQ-GRP-EN 83410228-QCI-CAN-EN 83410226-QCI-CAN-EN 83410233-QCI-CAN-EN 83410234-QCI-CAN-EN 83410231-QCI-CAN-EN
TCTS WBS.2.2 | Safety Assurance | All Safety Assurance activities performed at any stage and level of the project | Safety Assurance Safety Management (Transportation specific) Systems Integration, Verification, Validation and Qualification Lifecycle Process Description | 4.1 | 87211146-QCI-GRP-EN 83410196-QCI-CAN-EN 83410305-DDQ-CAN-EN
TCTS WBS.2.3 | RAMT | Activities related to the Specification and Demonstration of Dependability, Reliability, Availability, Maintainability and Safety (RAMS) | RAM Management Guideline for RAM Planning | 6.1 | 83410195-DDQ-CAN-EN 83410350-SER-CAN-EN
TCTS WBS.2.4 | Independent Validation | Activities related to the Independent Validation of the solution | Independent Validation Governance Instruction | 4.1 6.1 | 83410894-QCI-CAN-EN | Reference is (pending) governance instruction
TCTS WBS.3 | Solution Engineering
TCTS WBS.3.1 | Project Engineering Management |  | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN
TCTS WBS.3.2 | Solution Configuration Management
TCTS WBS.3.3 | Systems Engineering | Solution design activities (specification, system architecture, operational concepts) | Manage a Work Package Engineering reviews instruction Instruction for producing a Design & Justification File (D&JF) | 5.2 6.1 6.1 | 87201255-PRJ-GRP-EN 87201334-DDQ-GRP-EN 87201508-DDQ-GRP-EN
TCTS WBS.3.4 | Software Engineering | Gathers all SW Subsystem development activities according to DDQS, including cost collector for material procurement | Manage a Work Package Engineering reviews instruction Instruction for producing a Design & Justification File (D&JF) | 5.2 6.1 6.1 | 87201255-PRJ-GRP-EN 87201334-DDQ-GRP-EN 87201508-DDQ-GRP-EN
TCTS WBS.3.5 | Hardware Engineering | Hardware Work Package Includes Vehicle/Wayside & Central HW Gathers all Hardware development activities according to DDQS | Manage a Work Package Engineering reviews instruction Instruction for producing a Design & Justification File (D&JF) | 5.2 6.1 6.1 | 87201255-PRJ-GRP-EN 87201334-DDQ-GRP-EN 87201508-DDQ-GRP-EN
TCTS WBS.3.6 | Integration, Test and Verification | ITV is about verification, validation & qualification activities performed at System level - All subsytem ITV activities are in the subsystem work packages. | Manage a Work Package Engineering reviews instruction Instruction for producing a Design & Justification File (D&JF) Systems Integration, Verification, Validation and Qualification Handbook | 5.2 6.1 6.1 6.1 | 87201255-PRJ-GRP-EN 87201334-DDQ-GRP-EN 87201508-DDQ-GRP-EN 83410345-DDQ-CAN-EN
TCTS WBS.3.7 | Product / Platform | Platform & Product activities and commitment of the Product team towards the Project. | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN
TCTS WBS.4 | Data Communication Systems
TCTS WBS.4.1 | Cyber IT / DCS / Network / Tools Design | specialized domain knowledge on cybyersecurity engineering and assist system and other engineers develop and incorporate security design and functions into their solutions. | URS Cybersecurity Instruction | 0.1 | 83410893-GOV-CAN-EN
TCTS WBS.4.2 | DCS Test and Verification
TCTS WBS.4.3 | Cyber Security Assurance | Provides domain knowledge for conducting cybersecurity risk assessment, technical vulnerability assessment and penetration testing, security site acceptance testing
TCTS WBS.5 | Solutions Deployment |  | Site Deployment Handbook | 6.1 | 83410470-DDQ-CAN-EN
TCTS WBS.5.1 | Deployment Project Management | -WPM activities -Produce Operations & Maintenance Manuals Anything related to customer training -Activities related to any document to be ECN'd and drawings and SW archiving | Manage a Work Package Site Deployment Handbook Guideline | 5.2 | 87201255-PRJ-GRP-EN
TCTS WBS.5.2 | Installation Design | WPM activities | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN
TCTS WBS.5.3 | Warehouse & Logistic | WPM activities | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN
TCTS WBS.5.4 | Installation | All Wayside, Central & vehicle installation activities, including surveys, subcontractors management | Site Deployment Handbook Acceptance Review Description | 8.1 5.2 | 83410470-SER-CAN-EN 87202030-PRJ-GRP-EN
TCTS WBS.5.5 | Test & Commissioning | All Vehicle SPICO & SAT & commissionning activities, subbcontractors management, DPICO & SAT & commissionning, .. | Site Deployment Handbook Acceptance Review Description | 8.1 5.2 | 83410470-SER-CAN-EN 87202030-PRJ-GRP-EN
TCTS WBS.5.6 | Decomissioning | WPM activities | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN
TCTS WBS.5.7 | HSE | All Health, Safety & Environment activities | Project/Product HSE plan HSE Management System Guide (Sites & Operations) | 9.02 | 87204117-HSE-GRP-EN 87200107-HSE-GRP-EN
TCTS WBS.5.8 | Track and Civil Works | WPM activities | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN
TCTS WBS.5.9 | Training Delivery | -Produce Operations & Maintenance Manuals Anything related to customer training | Manage a Work Package Produce Customer Documentation Provide Customer training | 5.2 8.1 8.1 | 87201423-SER-GRP-EN 87201424-SER-CAN-EN 83410362-DOC-CAN-EN | Available on GTS MS Processes ->8.1 SER -> Produce Customer Documentation -> Print Available on GTS MS Processes ->8.1 SER -> Provide Customer training -> Print
TCTS WBS.6 | Service Delivery |  | Prepare and Deliver Customer Service CAN | 8.1 | 87201420-SER-GRP-EN | Available on GTS MS Processes -> 8.1 SER -> Print
TCTS WBS.6.1 | Test & Commissioning Support | WPM activities | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN 83410470-SER- CAN-EN
TCTS WBS.6.2 | Warranty Support | Activities related to provision of warranty services | Manage a Work Package Monitor availability and continuity of service Service Management Plan | 5.2 8.1 8.1 | 87201255-PRJ-GRP-EN 87201436-SER-GRP-EN 87208266-SER-GRP-EN
TCTS WBS.6.3 | Life Cycle Support | - Repair Management - Spare Parts Management - Service Engineering Management - Obsolescence Management | Manage a Work Package Repair equipment or systems Manage spares, consumables, materials Service Management Plan Guide for Obsolescence Management Plans | 5.2 8.1 8.1 8.1 8.1 | 87201255-PRJ-GRP-EN 87201428-SER-GRP-EN 87201430-SER-GRP-EN 87208266-SER-GRP-EN 83410348-SER-CAN-EN | Available on GTS MS Processes ->8.1 SER -> Repair equipment or systems -> Print Available on GTS MS Processes ->8.1 SER -> Manage spares, consumables, materials -> Print
TCTS WBS.6.3 | Other Services | WPM activities | Manage a Work Package | 5.2 | 87201255-PRJ-GRP-EN 83410470-SER- CAN-EN | Available on GTS MS Processes ->8.1 SER -> Repair equipment or systems -> Print Available on GTS MS Processes ->8.1 SER -> Manage spares, consumables, materials -> Print
Hitachi Rail – Internal
This document may not be reproduced, modified, adapted, published, translated, in any way, in whole or in part, or disclosed to a third party without the prior written consent of HITACHI RAIL
|  |  | © Hitachi Rail Limited 2025. All rights reserved. |  | Template: 87201589-QCI-GRP-EN-014
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @DELEVACQUE Thomas Remove TCTS references

## Generic OBS
Generic OBS for URS Projects
-
Hitachi Rail – Internal
This document may not be reproduced, modified, adapted, published, translated, in any way, in whole or in part, or disclosed to a third party without the prior written consent of HITACHI RAIL
| © Hitachi Rail Limited 2025. All rights reserved. | Template: 87201589-QCI-GRP-EN-014
(1*) Hardware Engineering Manager (HwEM) is handling Hardware activities for Vehicle, Wayside plus (Wayside/Central/DCS) and Tools HW. Depending on the Project complexity this role might be split in 1 to multiple WorkPackages Managers reporting to the Solution Engineering Manager.
(2*) Software Engineering Manager (SwEM) is handling Software activities for Vehicle, Wayside, DCS, Central, Simulation & Interlocking. Depending on the Project complexity this role might be split in 1 to multiple WorkPackages Managers reporting to the Solution Engineering Manager.
(3*) Training also encompasses Documentation Management, Publication & Data Records
(4*) Lifecycle Support encompasses the following Chorus' activities : Repair Management, Spare Parts Management, Service Engineering Management (SVEM), Obsolescence Management and Warranty Management.
(5*) Safety Lead and RAM Lead are considered to be the Specialists (SpE) required to attend DDQS gates.
(6*) Safety Assurance Manager (SAM) is the Technical Safety decision maker for all DDQ gates. For software and hardware level gates, the SAM role will normally be delegated to IVAL by the SAM.
(7*) Depending on the project size & complexity, the PSM and the Safety Engineering Lead roles can be performed by the same person.
(8*) if the Data Communication Systems WP is in WP3, the DCSM reports to the SEM. if it is in WP4, the DCSM will report to the PM.
(9*) Chief Engineering Architect is appointed exclusively on selected Bids or Projects that have high technical /engineering complexity or instability. He defines (with the PM) the technical and development organisation within the project. The Chief Engineer has overall responsibility over PDA and SEM activities. PDA and/or SEM roles can be allocated to the Chief Engineer when relevant.
The role of PPTM (Producttion Process Technology Managemt) is deemed not to be applicable to our business.
EMBEDDED VISIO DRAWING
Please note that the OBS revision number (top right) is to be kept for version traceablility.
For a definition of the Project Core team, please refer to the 83410863-PRJ-CAN-EN URS Project Progress Review Instructions

## Generic CBS
Generic CBS for URS Projects
-
Hitachi Rail – Internal
This document may not be reproduced, modified, adapted, published, translated, in any way, in whole or in part, or disclosed to a third party without the prior written consent of HITACHI RAIL
| © Hitachi Rail Limited 2025. All rights reserved. | Template: 87201589-QCI-GRP-EN-014
Please note that the CBS revision number (bottom right) is to be kept for version traceablility.
Data Communication Systems to be as WP4 only if:
- WP hours > 10% Eng hours
- WP hours > 5% total project hours
- Visible deliverables to the Customer
Otherwize it will be treated as WP3.8.
Decision to be taken at Bid Phase & confirmed at Project Launch Review.
*

## Generic RACI
Generic RACI Matrix for URS Projects
-
| Program Management | Program Management | Cost Control Management | Contract Management | Procurement | Quality Assurance | Publications & Archives | Technical Safety | Safety Engineering | Safety Assurance | RAMT | Independent Validation | Solution Engineering | Project Engineering Mgt | Solution CM | Systems Engineering | Software Engineering | Hardware Engineering | Integration, Test and Verification | Product / Platform | Data Communication Systems | Cyber IT / DCS / Network / Tools Design | DCS Test and Verification | Cyber Security Assurance | Solutions Deployment | Deployment Project Management | Infrastructure Design | Warehouse & Logistic | Installation | Test & Comissioning | Decommissioning | HSE | Track and Civil Works | Training Delivery | Service Delivery | Warranty Support | Life Cycle Support | Other Services
Project Manager |  | A/R | A | A | A | A | A |  | I | I | I | I |  | I | I | I | I | I | I | I |  | I (WP3) / A (WP4) | I (WP3) / A (WP4) | I (WP3) / A (WP4) |  | I | I | I | I | I | I | I | I | I |  | I | I | I
Project Office Manager |  | R | C |  |  |  | C
Data Manager |  | R |  |  |  |  | C
Publications WPM |  | C |  |  |  |  | R | [26 empty] | R
Administrative Assistant |  | C
Project Planner |  | R | C | [10 empty] | I | I
Risk & Opportunity Manager |  | R
Project Financial Controller |  | R | R
Contract Manager |  | C |  | R
Acquisition Project Manager |  | C |  |  | R | [21 empty] | C | R
Quality Assurance Manager |  | C |  |  |  | R
Project Configuration Manager |  | C |  |  |  |  | C | [6 empty] | C | R | C | C | C | C | C |  | C | C |  |  | C | C | [9 empty] | C
Safety Assurance Manager |  | C | [7 empty] | A/R
Project Safety Manager |  | C | [6 empty] | A/R |  | C
RAM Lead |  | C | [8 empty] | A/R
Localized Safety Manager |  | C | [6 empty] | R
Safety Authority |  | C | [9 empty] | C
Independent Validator |  | C | [9 empty] | A/R
Independent SW Assessor |  | C | [7 empty] | R
Independent Safety Assessor |  | C | [7 empty] | R
Cyber Security Authority |  | C | [16 empty] | C |  |  | C |  | A
Project Cybersecurity Manager (PCM) |  | C | [21 empty] | R
Chief Engineering Architect |  | C |  |  |  |  | C | [6 empty] | A | A | A | A | A | A | A |  | I (WP4) / A (WP3) | I (WP4) / A (WP3)
Solution Engineering Manager |  | C |  |  |  |  | C | [6 empty] | R | A | A | A | A | A | A |  | I (WP4) / A (WP3) | I (WP4) / A (WP3)
Solution Engineering Manager Product/Platform |  | C | [17 empty] | R
System WPM |  | C | [13 empty] | R |  |  | C |  |  | C
Data Communication Systems Manager |  | C | [19 empty] | R | R | R
Architect |  | C | [6 empty] | C |  | C |  |  |  |  | C |  |  | C |  |  | C
System Engineers |  | C |  |  |  |  | C |  | C |  | C |  |  |  |  | C |  |  | C |  |  | C
Project Design Authority |  | C |  |  |  |  | C |  | C |  | C | C |  | R | R | C | C | C | C |  |  | C | C
Project Design Authority Product/Platform |  | C | [17 empty] | R
HW Engineering Manager |  | C | [15 empty] | R | [10 empty] | I | I | I |  | I
HW Architect |  | C | [8 empty] | C | [6 empty] | C
HW Engineers |  | C | [15 empty] | C
HW CM Controller |  | C |  |  |  |  | C |  | C |  |  |  |  | C | C |  |  | C | C |  |  | C |  |  |  | C | C | C
SW Engineering Manager |  | C | [14 empty] | R
SW Architect |  | C | [6 empty] | C | [7 empty] | C
SW Engineers |  | C | [14 empty] | C
SW CM Controller |  | C |  |  |  |  | C |  | C |  |  |  |  | C | C |  | C
IVVQ Manager |  | C |  |  |  |  | C | [11 empty] | R |  |  |  | R | [5 empty] | I | I | I |  | I
HW IVQ Manager |  | C | [16 empty] | C |  |  |  | C
SW IV Manager |  | C | [16 empty] | C |  |  |  | C
Deployment Project Manager |  | C |  |  | C | [8 empty] | C | C | [8 empty] | C |  | A | A | A | A | A | A | A | A | A
SID WPM |  | C |  |  | C | [18 empty] | C |  |  | R
Site Deployment Lead |  | C | [24 empty] | C | R | R | R | R |  | R
Site Configuration Manager |  | C | [6 empty] | C | [9 empty] | C |  |  | C |  |  |  | C/R | C | C | C | C | [6 empty] | C
Subcontractor Manager |  | C | [24 empty] | C
HSE Manager |  | C | [29 empty] | R
Training |  | C | [31 empty] | R
Service Delivery Manager (SDM) |  | C | [33 empty] | A | A | A
Lifecycle Support |  | C | [33 empty] | R | R
Integrated Logistics Support |  | C | [34 empty] | R
(R)esponsible : Person in charge to perform a task
(A)ccountable : Person (sole) in charge of the FINAL decision
(C)onsulted : Person to be consulted upstream (to validate a part)
(I)nformed : Person to inform downstream
Comments:
1- This matrix is an example and it must be adapted to the concerned project. Some roles can be added or removed as needed.
2- The identified project roles identified in the RAM, WBS and OBS should be explicit and identical in all the 3 documents.
Hitachi Rail – Internal
This document may not be reproduced, modified, adapted, published, translated, in any way, in whole or in part, or disclosed to a third party without the prior written consent of HITACHI RAIL
[10 empty] | © Hitachi Rail Limited 2025. All rights reserved. |  |  |  |  | Template: 87201589-QCI-GRP-EN-014